## Management Plan
(Project Title)
Comments | Status | Date | Priority | Tasks | Description | Deliverable(s) | Deadline | % Done | ***Please include a brief description of how you plan to execute the outlined tasks in the box below***
| - |  | - | [ Task 1 ] | [ Details ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Task 2 ] | [ Details ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Task 3 ] | [ Details ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Task 4 ] | [ Details ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Task 5 ] | [ Details ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]
| - |  | - | [ Sub Task ]

## Example Project
Campus Recycling Bin Expansion Project
Comments | Status | Date | Priority | Tasks | Description | Deliverable(s) | Deadline | % Done
| Completed |  | - | Assemble Team
| Completed |  | done | Contact External Partners (OSU) | Communicate with FOD about exisiting recycling operations |  | 2019-02-15 | 100%
| Completed |  | done | Contact Bin Supplier | Obtain pricing figures |  | 2019-02-15 | 100%
| - |  | - | Locate Optimal Bin Location
Process will continue after spring break | In Progress |  | high | Perform exisitng recycling bin survey on Campus | Locate current bin locations within targeted area |  | 2019-03-20 | 50%
| In Progress |  | high | Determine optimal location for new bins | locating areas across campus where there are fewer places to properly recycle materials |  | 2019-04-15 | 10%
| Pending Review |  | - | Present findings to OSU for approval |  |  | 2019-04-16 | 0%
| - |  | - | Install New Bins
| - |  | - | Acquire bins from supplier |  |  | 2019-05-01 | 0%
| - |  | - | Enact Phase 1 of Installs |  |  | 2019-05-10 | 0%
| - |  | - | Enact Phase 2 of Installs |  |  | 2019-05-20 | 0%
| - |  | - | Enact Phase 3 of Installs |  |  | 2019-05-30 | 0%
| - |  |  | Inform OSU/OSEP of Project Completion |  |  | 2019-06-03 | 0%

## Settings
Priorities | Status
- | -
high | Planning
med | Pending Approval
low | Approved
done | In Progress
Pending Review
On Hold
Completed